## Check 10
Activity | a | 4m | b | Activity | LS | ES | Slack | Activity | Expected t (a+4m+b)/6 | Variance ((b-a)/6)^2
A | 0.5 | 1 | 2 | A | 0 | 0 | 0 | A | 0 | 0.0625
B | 1 | 2 | 2.5 | B | 4 | 3 | 1 | B | 4
C | 2.5 | 3 | 3.5 | C | 1 | 1 | 0 | C | 1 | 0.027778
D | 1 | 2 | 3 | D | 4 | 3 | 1 | D | 4
E | 0.9 | 1 | 1.1 | E | 4 | 4 | 0 | E | 4 | 0.0011111
F | 0.5 | 1 | 1.5 | F | 5 | 5 | 0 | F | 5 | 0.027778
0.11917
0.34525
1.448
0.92619
Problem 10
Workspace
Back
Check Problem 10
Solution
Back
Project Variance
Project SD
z score
Probability
Given the following information calculate the probability that this project can be completed in 6.5 day.
The average (expected) completion time was calculated in the problem 9. It is 6 days.

## 10
Activity | a | 4m | b | Activity | LS | ES | Slack
A | 0.5 | 1 | 2 | A | 0 | 0 | 0
B | 1 | 2 | 2.5 | B | 4 | 3 | 1
C | 2.5 | 3 | 3.5 | C | 1 | 1 | 0
D | 1 | 2 | 3 | D | 4 | 3 | 1
E | 0.9 | 1 | 1.1 | E | 4 | 4 | 0
F | 0.5 | 1 | 1.5 | F | 5 | 5 | 0
Problem 10
Workspace
Back
Check
Problem 10
Back
Given the following information calculate the probability that this project can be completed in 6.5 day.
The average (expected) completion time was calculated in the problem 9. It is 6 days.

## 9
Activity | Predecessor(s) | Duration (Days)
A |  | 1
B | A | 2
C | A | 3
D | B | 2
E | B,C | 1
F | D,E | 1
Problem 9
Workspace
Back
PERT Expected Completion Time.
Given the following information calculate the Expected completion time for this project.
.
Check

## Check 9
|  |  | A | ES | EF
|  |  | t | LS | LF
[6 empty] | B | 1 | 3 | D | 3 | 5
[6 empty] | 2 | 1 | 3 | 2 | 3 | 5
Activity | Predecessor(s) | Duration (Days)
A |  | 1 | A | 0 | 1 | [6 empty] | F | 6 | 7
B | A | 2 | 1 | 0 | 1 | [6 empty] | 1 | 6 | 7
C | A | 3
D | B | 2 |  |  |  | C | 1 | 4 | E | 4 | 6
E | B,C | 2 |  |  |  | 3 | 1 | 4 | 2 | 4 | 6
F | D,E | 1
Check Problem 9
Solution
Back
PERT Expected Completion Time.
Given the following information calculate the Expected completion time for this project.
.
Reference Template

## Check 12
Variables | X1 | X2 |  | Available
Assembly time | 4 | 10 |  | 100
Inspection time | 2 | 1 |  | 22
Storage requirements | 3 | 3 |  | 39
Profit per unit | 60 | 50
Variables Variables
| X1 | X2
Types to be produced | 9 | 4
Profit | 740
Constraints | LHS |  | RHS
Assembly | 76 | ≤ | 100
Inspection | 22 | ≤ | 22
Storage | 39 | ≤ | 39
Check Problem 2
Workspace
Back
Given the following mathematical model use Solver to calculate the values of x1 and x2
The mathematical model is:
x1 = quantity of type 1 to be produced
x2 = quantity of type 2 to be produced
Maximize: 60X1 + 50X2
Subject to:
Assembly: 4X1 +10X2 ≤ 100 hours
Inspection: 2X1 + 1X2 ≤ 22 hours
Storage: 3X1 + 3X2 ≤ 39 cubic feet
Conditions of non-negativity:
x1, x2 ≥ 0
Givens:
Model

## 12
Problem 2
Workspace
Back
Given the following mathematical model use Solver to calculate the values of x1 and x2
The mathematical model is:
x1 = quantity of type 1 to be produced
x2 = quantity of type 2 to be produced
Maximize: 60X1 + 50X2
Subject to:
Assembly: 4X1 +10X2 ≤ 100 hours
Inspection: 2X1 + 1X2 ≤ 22 hours
Storage: 3X1 + 3X2 ≤ 39 cubic feet
Conditions of non-negativity:
x1, x2 ≥ 0
Check

## Check 11
| Type 1 | Type 2
Profit per unity | 60 | 50
Assembly time per unit | 4 hours | 10 hours
Inspection time per unit | 2 hours | 1 hour
Storage space per unit | 3 cubic feet | 3 cubic feet
Resource | Amount Available
Assembly time | 100 hours
Inspection time | 22 hours
Storage space per unit | 39 cubic feet
Check Problem 1
Workspace
Back
Available resources:
All computers produced can be sold.
The mathematical model is:
x1 = quantity of type 1 to be produced
x2 = quantity of typr 2 to be produced
Maximize: 60X1 + 50X2
Subject to:
Assembly: 4X1 +10X2 ≤ 100 hours
Inspection: 2X1 + 1X2 ≤ 22 hours
Storage: 3X1 + 3X2 ≤ 39 cubic feet
Conditions of non-negativity:
x1, x2 ≥ 0
Stevenson 282
A firm that assembles computers and computer equipment is about to start production of two new types of microcomputers (Type 1 and Type 2).
Each type will require assembly time. inspection time, and storage space.
The amounts of each of these resources that can be devoted to the production of the microcomputers is limited.
The manager of the firm would like to determinate the quantity of each microcomputer to produce in order to maximize the profit generated by sales of these microcomputers.
Write the mathematical representation of this problem.
The following information were collected from the operations department of this firm:

## Check 1
| # of customers arriving | Probability | Cumulative Probability | Interval
| 0 | 0.55 | 0.55 | 0.00 to 0.55
| 1 | 0.25 | 0.8 | 0.56 to 0.80
| 2 | 0.15 | 0.95 | 0.81 to 0.95
| 3 | 0.05 | 1 | 0.96 to 1.00
1
|  | Period | Random Numbers |  | Simulated Arrivals
|  | 1 | 63 |  | 1
|  | 2 | 27 |  | 0
|  | 3 | 15 |  | 0
|  | 4 | 99 |  | 3
|  | 5 | 86 |  | 2
|  | 6 | 71 |  | 1
|  | 7 | 74 |  | 1
|  | 8 | 45 |  | 0
|  | 9 | 11 |  | 0
|  | 10 | 2 |  | 0
8
121
Check Problem 1
Solution
Back
Simulate the number of customers that arrive during a 10-minute period.
Total Arrivals in 10 minutes

## FirstPage
BUS 322
Click Here to Start
Pretest 3 LP

## 11
| Type 1 | Type 2
Profit per unity | 60 | 50
Assembly time per unit | 4 hours | 10 hours
Inspection time per unit | 2 hours | 1 hour
Storage space per unit | 3 cubic feet | 3 cubic feet
Resource | Amount Available
Assembly time | 100 hours
Inspection time | 22 hours
Storage space per unit | 39 cubic feet
Problem 1
Workspace
Back
Check
Stevenson 282
A firm that assembles computers and computer equipment is about to start production of two new types of microcomputers (Type 1 and Type 2).
Each type will require assembly time. inspection time, and storage space.
The amounts of each of these resources that can be devoted to the production of the microcomputers is limited.
The manager of the firm would like to determinate the quantity of each microcomputer to produce in order to maximize the profit generated by sales of these microcomputers.
Write the mathematical representation of this problem.
The following information were collected from the operations department of this firm:
Available resources:
All computers produced can be sold.

## Content Master
BUS 322 Pretest 3 LP
Content
Back
LP Problem 1
LP Problem 2