## CheckCarlston (2) (hidden)
0
79
|  | Original Nodes |  | Destination Nodes
Transportation Cost per Unit
D1=1,100
S1=1,200
D2=400
S2=1,000
D3=750
S3=800
D4=750
Carlston Pharmaceuticals
Back
1
Cleveland
2
Detroit
3
Greensboro
1
Boston
2
Richmond
3
Atlanta
4
St.Louis
35
30
40
32
40
15
20
28
37
40
42
25
Assumptions:
In order to solve for the optimal shipping pattern, we make several simplifying assumptions so that it meets the criteria of a basic transportation model.
1. The per item shipping cost remains constant, regardless of the number of units shipped.
2. All the shippingg from the sources to the destinations occurs simultaneously.
3. The vaccine an be shipped only between sources and destinations.
Solution Structure:
Origin
1=Cleveland
2=Detroit
3=Greensboro
Destination
1=Boston
2=Richmond
3=Atlanta
4=St.Louis
Xij= the number of cases shipped from plant "i" to warehouse "j"
MIN 35X11+30X12+40X113+32X14+37X21+40X22+42X23+25X24+40X31+15X32+20X33+28X34
s.t.
X11+X12+X13+X14≤ 1,200
X21+X22+X23+X24≤ 1,000
X31+X32+X33+X34≤ 800
X11+X21+X31= 1,100
X12+ X22+ X32= 400
X13+ X23+ X33= 750
X14+ X24+X34= 750
xIJ≥0,for all i and j

## FirstPage
Operations Management
Project Management
Sample Problems
Click Here to Start

## Content
Project Management
PERT
GANTT
Content
Back
Glossary

## Key
A | 9 11
2 | 13 15
Key
Back
Step
Duration of the Step
Earliest Start Time
Earliest Finish Time
Latest Start Time
Latest Finish Time

## PERT
Activity | Earliest Start (ES) | Latest Start (LS) | Earliest Finish (EF) | Latest Finish (LF) | Slack | Critical Path |  | Optimistic, Most probable, and pessimistic Activity time Estimates (in Weeks)
(LS-ES)
A | 0 | 0 | 6 | 6 | 0 | X |  | Activity | Optimistic (a) | Most Probable (m) | Pessimistic (b) | Variance
B | 0 | 7 | 2 | 9 | 7 |  |  | A | 4 | 5 | 12 | 1.7778
C | 6 | 10 | 9 | 13 | 4 |  |  | B | 1 | 1.5 | 5
D | 6 | 7 | 11 | 12 | 1 |  |  | C | 2 | 3 | 4
E | 6 | 6 | 9 | 9 | 0 | X |  | D | 3 | 4 | 11
F | 9 | 13 | 11 | 15 | 4 |  |  | E | 2 | 3 | 4 | 0.11111
G | 11 | 12 | 14 | 15 | 1 |  |  | F | 1.5 | 2 | 2.5
H | 9 | 9 | 13 | 13 | 0 | X |  | G | 1.5 | 3 | 4.5
I | 13 | 13 | 15 | 15 | 0 | X |  | H | 2.5 | 3.5 | 7.5 | 0.69444
J | 15 | 15 | 17 | 17 | 0 | X |  | I | 1.5 | 2 | 2.5 | 0.027778
[8 empty] | J | 1 | 2 | 3 | 0.11111
2.7222
1.6499
[7 empty] | 1.8182 | [5 empty] | μ
[7 empty] | 0.96562 | 0.96562
Problem 1-PERT
Back
Critical Path: A - E - H - I - J
The latest finish time is 17 weeks. This is the X in the z-score formula.
Variance = ((b-a)/6)^2
b = pessimistic time estimate
a = optimistic time estimate
Total Critical Path Variance = 1.78 + 0.11 + 0.69 + 0.03 + 0.11 = 2.72
Standard Deviation = σ = SQRT(Variance)
σ = SQRT(2.72) = 1.65
Standardized z score
z = (20-17)/1.65
z = 1.82
The Probability of the project meeting the 20 week deadline is 0.9656
Step 3: Calculate variances of steps on the Critical Path using the formula ((b-a)/6))^2
Step 4. This is the sum of these individual variances.
Step 5. This is the square root of the number that was calculated in the Step 4.
Step 1. The value of 17 weeks is given.
Step 2. The steps that have slack = 0 are on the critical path.
Slack = LS-ES
Step 6. This is the z score calculated using the formula
(20 weeks- mean)/standard deviation
Step 7. Use NORM.S.DIST (z,1) to calculate the probability of completing this project within 20 weeks.

## GANTT
GANTT PROJECT SCHEDULE
| Step | Activity | Duration (in weeks) | 1
2
| 1 | Contract negotiated | 3 | 3
| 2 | Contract signed | 2 | 4
| 3 | Long Lead Procurement | 6 | 5
| 4 | Manufacturing Schedules Prep. | 4 | 6
| 5 | Bill of Material Prep. | 2 | 7
| 6 | Short Lead Procurement | 3 | 8
| 7 | Material Specifications Finalized | 2 | 9
| 8 | Processes Finalized | 5 | 10
| 9 | Production Process Test | 2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| 10 | Production Start-up | 1
Step | Predecessor | Activity | Duration (in weeks) |  | 1: GANTT PROJECT SCHEDULE
A |  | Contract negotiated | 3
B |  | Contract finalized | 2 | A | bar: 1 to 3
C | A | Long Lead Procurement | 6 | B | bar: 1 to 2
D | A, B | Manufacturing Schedules Prep. | 4 | C | bar: 4 to 9
D | bar: 10 to 13
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Problem 2 - GANTT
Draw a GANTT Chart based on the following information:
Solution
Back
Duration (in Weeks)
Steps
What is the expected duration of this project?
The expected duration of this project is 30 weeks.
Note: The next step can only start when the previous step or steps are completed.
These previous steps are called predecessors. See example below:
Steps

## Glossary
Project Management: Glossary
Back
1. PERT-Program Evaluation and Review Technique. A network technique that allows three time estimates for each activity in a project.
2. Activity-A time consuming job or task that is a key subpart of the total project.
3. Event-A point in time that mark the beginning or ending of an activity.
4. Immediate Predecessor -An activity that must be completed before activity can be started.
5. Network-A graphical display of a project that contains both activities and events.
6. Activity Time Estimates -Three time estimates that are used in determining the expected completion time and variance for an activity in a PERT network.
7. Optimistic Time(a) -The shortest amount time that could be required to complete the activity.
8. Pessimistic time (b) -The greatest amount of time that could be required to complete the activity.
9. Most Likely Time (m) -The amount of time that would be expected it would take to complete the activity.
10. Expected Activity Time -The average time it should take to complete an activity, t=(a+4m+b)/6
11. Earliest Start Time (ES) -The earliest time an activity can start without violation of precedence requirements.
12. Earliest Finish Time (EF) -The earliest time that an activity can be finished without violation of precedence requirements.
13. Latest Start time (LS) -The latest time that an activity can be started without delaying the entire project.
14. Latest Finish Time (LF) -The latest time that an activity can be finished without delaying the entire project.
15. Forward Pass -A procedure that moves from the beginning of a network to the end of the network. It is used to determine the latest finish and start times.
16. Slack Time - A amount of time that an activity can be delayed without delaying the entire project. Slack is equal to the latest start time-the earliest start time, or the latest finish time minus the earliest finish time.
17. Critical Path -The series of activities that have a zero slack. it is the longest time path through the network. A delay for any activity that is on the critical path will delay the completion of the entire project.
18. Dummy Activity - a fictitious activity that consumes no time and is inserted into a network to make the network display the proper predecessor relationship between activities.
19. CPM - A deterministic network technique that is similar to PERT but allows for project crashing.
20. Crashing -The process of reducing the total time that it takes to complete a project by expanding additional funds.